## Summary
Testing | Hours Estimated | Actual Hours (you need to track them)
Functional Testing | 15 | 8
Regression Testing | 2 | 2
Automation Testing | 5 | 3
Data preparation | 5 | 4
Bug verification | 3 | 4
Test case writing | 2 | 1
Test case review with Dev | 1 | 2
Other
Training from DEV | 10 | 9
Preparing this plan | 3 | 4
Sum before Risk | 46 | 37
Risk (10%) | 4.6 | 3.7
Total hours | 50.6 | 40.7

## Requirements
Requirement ID | Title | Hours testing | Type | Actual hours
1 | Selenium web-Driver | 10 | Driver | 8
2 | Nunit | 5 | Platform | 7
3 | C# | 20 | IDE | 18
4 | Javascript | 6 | Scripting Language | 5
5 | Html | 3 | Scripting Language | 4
Total Functional |  | 44 |  | 42

## Testers
.8 percent for testing
Work hours
Tester1 | Md Saurav Khan | 32
Tester2 | Abhinaya | 32
Test Lead | Md Saurav Khan | 32

## Environment
| Operating System | Browser
Laptop | Windows 10 | Chrome
MS Teams | Windows 10
Visual Studio 2019 | Windows 10
Ms Excel | Windows 10
Notepad(HTML documentation) | Windows 10
Ms Word | Windows 10

## Risk
|  | Level of damage | Action Plan
Risk1 | System failure | High | Backup of all the coding in cloud
Risk2 | Internet failure | Low | Backup connection
Risk3 | Employee fall sick | Medium | Take extra days
Risk4 | Test failure | High | Consult with developer

## Testing Strategy
Testing Types
Manual Testing
Automation Testing(Selenium)
Regression Testing
Functional Testing